## Pending
Project Number | Action Items - OCTOBER 1, 2020 | Priority | Entry Date | Start Date | Status | Comments/Updates
2019
SWM 2019-2 | Consider Policy Recommendations on storm drains off homes along ponds and whether HOA should install boxes and pipes between homes | Medium | 2019-07-01 |  | Pending | A draft policy has been developed and will be refined by the end of the year.
SWM 2019-9 | Maintain Dry Pond 5 in the Links | High | 2019-06-01 |  | In Process | Dry pond 5 in the Links is one of three prime projects for evaluation by a Professional Engineer, which will be presented to the BOD once received. The pond is not operating effectively and residents continue to have concerns.
SWM 2019-15 | Smell/Odor from Pond 10 (Irrigation Pond) in the Legacy Section | High | 2019-09-20 |  | Pending | Committee will explore several options for water quality, including pond airation, once the pond bank and flooding issues in item 2019-16 are addressed.
SWM 2019-16 | Review lake bank issues on pond 10 (irrigation lake). | High | 2019-04-25 |  | Pending | Pond Bank needs to be evaluated by a PE to determine what level of bank erosion has occurred, what is causing bank erosion, and what solutions are viable. Shroyer Drapola has been out to review the pond; awaiting GFY,Inc. input.
2020
SWM 2020-01 | Grate and Rebuild of Drain Outflow Box at SW corner of Lot C-15 at 5326 97th St. Cir. E. | High | 2020-03-06 |  | Completed | A-Team completed repair and rebuild next to 5326 97th St.Cir.E. The repair of the box required the removal of landscape ties and a tree, and then the replacement with a concrete wall. The homeowner had to water the newly laid sod and that cost was not provided for in the previous approval, and the homeowner has been asked to submit that to the committee. Railings and plantings are required to ensure safety of residents.
SWM 2020-02 | Address Swales Missing in Links | High | 2020-03-07 |  | Pending | Inventory of lot locations where center-line swales are on the plans has been completed, and each lot was checked to see if the swale is present or missing. Need to complete the same for property-line swales. This also relates to the work to be done by PE. SWM Com. members met with Lennar and SWFWMD and with Ashton Woods staff to review missing swales. Additional contact will be made with remaining builders.
SWM 2020-04 | Pond Bank between 5145 and 5203 96th St. | Low | 2020-06-07 |  |  | Severe Pond Bank erosion because of runoff from homes. Committee will consider.
SWM 2020-05 | Drain Pipe behind 8724 52nd Drive E. on Pond 12 | High | 2020-06-15 |  | Pending | Soil at top of drain into Pond 12 from street has eroded. Awaiting Aquagenix evaluation.
SWM 2020-06 | Pond Bank Erosion Pond 2 Legacy | Low | 2020-06-14 |  |  | Homeowner concern with pond bank erosion. Committee will review and possibly add plants.
SWM 2020-07 | Pond Plantings | Medium | 2020-07-01 |  | Pending | Committee members will identify additional ponds requiring aquatic plantings.
SWM 2020-08 | Removal of Invasive Vegetation in Wetland Buffer/Conservation Areas | Medium | 2020-07-01 |  | Pending | Committee members will evaluate and identify additional areas that require invasive removal.
SWM 2020-09 | Regrading of HOA Easement behind homes on 96th St and along 11th Fairway | Low | 2019-04-01 | 2019-07-01 | Partialy Completed | Riprap was added to eroded section just north and west of Highland circle in July 2020. Further work on the drainage behind homes along 96th St and 11th Fairway will require PE evaluation to identify solutions. This is a follow-on project from 2019 (SWM 2019-5).
SWM 2020-10 | Evaluate Whether Pond 11 Legacy Water Level Can Be Raised | Low | 2020-06-25 |  |  | Residents have asked that the pond water level be raised and that weeds in the pond be elminated. The water level is dictated by SWFWMD engineering going back 25+ years and will require evaluation by a PE. Aquagenix has been notified of the need to take more agressive action to control aquatic weeds.

## Completed
Project Number | Action Items - Completed | Committee | Priority | Entry Date | Start Date | Status | Comments/Updates
SWC 2019-1 | Repair of Pond 4 (Westbury S) pond banks. |  | High | 2019-05-01 |  | Completed | Aquagenix completed installation of erosion fabric and riprap along common ground sections of Pond 4 because of high water level. Board is asked, at its August 2020 meeting, to approve $1,000 for additional work done on mitered pipe ends to shore them up while doing the riprap.
SWM 2019-3 | Pond Plantings | Stormwater | Medium | 2019-05-01 |  | Completed | Committee will consider locations of pond plantings for Highlands and Legacy ponds this summer and will include requirements in 2021 budget request.
SWM 2019-4 | Renewal of SWFWMD Permit 53.3 | Stormwater | High | 2019-07-01 | 2019-09-01 | Completed: 10-2019 | Contracted with Kinney Engineering, and Kinney requested SWFWMD extention until 11-9-19. On site visit was on October 5th; two issues had to be corrected and were completed by Oct. 19 and pictures submitted to Kinney. Permit record has been updated in SWFWMD records.
SWM 2019-5 | Regrading of HOA Easement behind homes on 96th St and along 11th Fairway |  | Low | 2019-04-01 | 2019-07-01 | Partialy Completed - Remainder to 2020-9 | Riprap was added to eroded section just north and west of Highland circle in July 2020. Further work on the drainage behind homes along 96th St and 11th Fairway will require PE evaluation to identify solutions, and this portion of the work will be moved to the 2020 project listing as SWM 2020-09.
SWM 2019-6 | Repair Weir, Sump Area behind 5308 88th St E. | Stormwater | High | 2019-05-01 | 2019-07-15 | Completed: Nov. 2019 | Contract Awarded; work was to begin in early July. Work completed week of Oct. 14 in conjunction with repair required under SWM 2019-4.
SWM 2019-7 | Update Committee Charter | Stormwater | High | 2019-07-03 | 2019-07-08 | Completed | Based on BOD request, the Committee has considered a new charter and forwarded it on the the Board.
SWM 2019-8 | Review platted swales to determine if they are present (Issue w/ Links Lots 178-182) | Stormwater | High | 2019-04-01 |  | Completed; Moved to #2020-2&3) | The PE services are needed to address missing swales in the Links, and recommendations on this will be presented to the BOD in July. There are 107 home sites that require swales, and an inventory of which homes have swales and which don't will be conducted in July by Committee staff.
SWM 2019-10 | Obtain Lake Erosion Management Study | Stormwater | Medium | 2019-06-01 | 2019-07-01 | Completed: Oct 2019 | Purchase agreement approved; work was to begin in early July. Vendor has been delayed in getting report completed. Vendor met with Com. Chair on Oct. 3 and provided the report. The report was shared with SWM Com., Mgt. Com. and BOD. This project is complete and the report will be used to prioritize work and repairs on pond banks.
SWM 2019-11 | Evaluate 8602 51st Terrace E. lake bank | Stormwater | High | 2019-03-28 | 2019-03-28 | Completed: June 2019 | Reviewed plat and obtained lot survey; determined erosion of area behind home was homeowner responsibility; communicated with homeowner on 6-30-2019
SWM 2019-12 | Removal of Vegetation along 11th Fairway north of homes on 96th St. | Stormwater | Medium | 2019-02-01 |  | Completed: Nov 2019 | Approved by BOD on 7/03/2019; Work to be done by Teal. Teal completed work in early November.
SWM 2019-13 | Evaluate Removal of Invasive Vegetation in Wetland Areas | Stormwater | Medium | 2019-02-01 |  | Completed; Added Similar Requirement for 2021 for three other areas of Rosedale | Crosscreek Environmental has completed invasive removal work on the Red section.
SWM 2019-14 | Bulkhead Repair 8738 to 8746 & 8743 to 8749 53rd Ter.E. |  | High | 2019-07-15 |  | Completed | Aauagenix completed work in July to add riprap at the end of each bulkhead where it meets slopped pond bank to prevent erosion of pond bank.
SWM 2019-17 | Golf Course Request to Reduce Pond Levels | SWM | Low | 2019-09-16 |  | Never Responded to and Removed from Pending on 6-1-20 | Letter was sent to CH6 in December 2019 asking that it identify pond numbers and levels requested, along with request on Pond 10 water quality and advising of bulkhead repairs. No written response has been received, but Chris Schaeffer has indicated a willingness to meet with Lynne Woodman and Bill Moran, and that meeting still needs to be set up.
SWM 2019-18 | Request for Approval of Allow Pond Grass to Grow 18-24 inches from pond edge at a height of 12-18 inches | SWM | Medium | 2019-10-12 |  | Completed: Nov 2019 | Drafted a policy recommendation for consideration by BOD at is Nov. 2019 meeting, and it was approved. Committee will monitor this pond to see if it helps erosion and pond health.
SWM 2019-19 | Oppose the County Stormwater Mgt. Assessment Proposal | SWM | High | 2019-09-24 |  |  | Action on proposal deferred by County until February 2020. Awaiting additional information.
SWM 2020-03 | Address Issues in PE report on Links SWM system (other than swales) |  | High | 2020-03-07 |  | Completed | Aquagenix completed work in July on skimmer cleanout on 3 ponds and removal of netting in all Links ponds.